## Gap Matrix
Requirement Area | PRD Expectation | Current Demo Status | Gap | Recommended Phase | Complexity
Core app architecture | Frontend + backend + orchestration + DB + provider layer | Implemented in simplified form | Mostly aligned | Current | Low
Prompt Transformer in middle | Personalized prompt orchestration layer | Implemented | Strong alignment | Current | Low
Standalone app | Standalone app supported | Implemented | Aligned | Current | Low
Softr embed support | Softr embeddable with secure session handling | iframe-friendly only | Missing real Softr integration/session handling | Phase 2 | Medium
Authentication | Softr session auth + standalone login | Not implemented | Major gap | Phase 2 | High
User identity model | Email/auth identity mapped to internal user_id_hash | Query-string user_id_hash only | Major gap | Phase 2 | Medium
Chat interface | Primary chat interface | Implemented | Aligned | Current | Low
Profile card panel | Read-only user profile card | Not implemented | Full gap | Phase 3 | Medium
Prompt Builder UI | WHO / WHY / HOW / WHAT structured builder | Not implemented | Full gap | Phase 3 | High
Conversation history sidebar | Sidebar with saved threads | Not implemented | Full gap | Phase 2 | High
Persistent conversations | Persist chat history across sessions | Not implemented | Major gap | Phase 2 | High
Multi-conversation support | Multiple threads per user | Not implemented | Major gap | Phase 2 | High
Reopen/continue threads | Resume prior conversations | Not implemented | Major gap | Phase 2 | Medium
Rename/archive/delete | Admin-controlled thread management | Not implemented | Full gap | Phase 3 | Medium
Export chats | PDF and plain text export | Not implemented | Full gap | Phase 3 | Medium
Personalization engine | CQI + neuroscience-driven personalization | Simplified Prompt Transformer persona layer only | Partial alignment | Phase 3 | High
CQI data integration | CQI allowlist-backed personalization | Not implemented in app | Major gap | Phase 3 | High
Airtable integration | Airtable as source of truth in Phase 1 | Not implemented | Full gap | Phase 3 | High
SQL migration path | Airtable to SQL transition | Only partially reflected architecturally | Major gap | Phase 3 | High
Structured prompt coaching | WHO/WHY/HOW/WHAT/refinement/execution flow | Not implemented | Full gap | Phase 3 | High
Personalized questioning | Adaptive coaching questions, max 5 | Not implemented | Full gap | Phase 3 | Medium
Admin toggle for coaching | Admin-controlled enablement | Not implemented | Full gap | Phase 4 | Medium
Knowledge system | User/company/global knowledge | Not implemented | Full gap | Phase 4 | High
Conversation context as knowledge | Use conversation context in prompt stack | Partially implemented | Partial gap | Phase 2 | Low
Retrieval layer | Keyword + metadata retrieval in Phase 1 | Not implemented | Full gap | Phase 4 | High
Citations | Stored internally, optional display | Not implemented | Full gap | Phase 4 | Medium
Multi-LLM provider layer | OpenAI + Anthropic, admin-selected | OpenAI only, provider adapter started | Partial gap | Phase 2 | Medium
Fallback routing | Provider fallback routing | Not implemented | Full gap | Phase 4 | Medium
Hidden provider selection | Admin controlled, not user visible | Not implemented | Full gap | Phase 2 | Medium
Prompt orchestration stack | System + guardrails + user data + knowledge + history + input | Partial stack only | Significant gap | Phase 4 | Medium
Output: text | Text responses | Implemented | Aligned | Current | Low
Output: reports/tables/html | Rich formatted outputs including Softr-compatible HTML | Not implemented | Full gap | Phase 4 | High
HTML output support | Clean HTML/CSS blocks with usage notes | Not implemented | Full gap | Phase 4 | High
Action framework | Notes, Airtable updates, emails, webhooks | Not implemented | Full gap | Phase 5 | High
Action governance | Admin controlled, validated, logged, confirmed | Not implemented | Full gap | Phase 5 | High
Admin portal | Model config, prompt editing, knowledge, retention, permissions, analytics | Not implemented | Full gap | Phase 4 | High
Support mode | Admins can view conversations and troubleshoot | Not implemented | Full gap | Phase 4 | High
RBAC | Role-based access | Not implemented | Full gap | Phase 4 | High
Audit logging | Audit trail for admin/support/actions | Not implemented | Full gap | Phase 4 | High
Database model | Users, profiles, conversations, messages, knowledge, actions, logs, admin settings | Only feedback persistence and transformer profile DB exist separately | Major gap | Phase 2-5 | High
File attachments | Future-ready architecture | Implemented ahead of PRD | Ahead of requirement | Current | Medium
Image upload/analysis | Not explicit in PRD but aligned with future-ready multimodal direction | Implemented partially | Ahead of PRD | Current | Medium
Image generation | Not explicit in PRD | Partially implemented/OpenAI-specific | Experimental | Current | Medium
Security | PII protection, tenant isolation, prompt injection safeguards | Minimal only | Major gap | Phase 4 | High
Analytics | Usage, conversations, errors, provider usage, latency | Not implemented | Full gap | Phase 4 | Medium
Maintainability/modularity | Modular, extensible, vendor-neutral | Good early alignment | Partial | Current | Low
Admin/provider config | Admin function to select provider/model | Not implemented yet | Full gap | Phase 2 | Medium